AI SOFTWARE CO-AGENT

PROJECT PLAN & PROGRESS SPECIFICATION

Version 1.0 — FINAL / LOCKED

Document ID: PPP-001 • Implementation control baseline for the AI Software Co-Agent

| Field | Value |
| --- | --- |
| Document | Project Plan & Progress Specification |
| Version | v1.0 |
| Status | FINAL / LOCKED |
| Product | AI Software Co-Agent |
| Purpose | Control implementation sequencing, dependencies, milestones, progress, risks, decisions, validation and release readiness |
| Planning authority | This document governs project execution order; locked architecture/specification documents govern technical behavior |

Lock Statement: Project Plan & Progress Specification v1.0 is the final locked implementation-control baseline. It prevents phase skipping, undocumented scope expansion, dependency violations and false progress. Technical specifications remain authoritative for system behavior.

# 1. Purpose & Planning Mission

This document converts the locked specification set into a controlled implementation roadmap. It defines what must be built, in what order, what evidence marks progress, which dependencies must be satisfied, and how implementation is stopped or re-planned when blockers arise.

Primary planning principle: Never mark work complete merely because code exists; completion requires the defined evidence and validation gates.

# 2. Planning Principles

Specifications are the source of truth for intended system behavior.

Implementation follows dependency order, not convenience order.

Each phase has entry criteria, deliverables, validation and exit criteria.

Do not skip security or validation gates to accelerate progress.

Keep implementation scope aligned with the locked baseline.

Track blockers explicitly; do not hide them as partial completion.

Prefer small, testable increments.

Integrate borrowed/open-source patterns only after architectural fit and license/security review.

Every material implementation decision is recorded.

Progress must be evidence-based.

Changes to locked behavior require change control.

Keep repository structure and documentation synchronized.

Do not start broad optimization before correctness and safety are established.

# 3. Master 19-Document Baseline

| # | Document / Baseline | Role in implementation | Status |
| --- | --- | --- | --- |
| 01 | PRD v1.0 | Product goals, scope, users, success criteria | FINAL / LOCKED |
| 02 | SRS v1.0 | Functional/non-functional requirements | FINAL / LOCKED |
| 03 | System Architecture v1.0 | System boundaries and components | FINAL / LOCKED |
| 04 | Technical Design v1.0 | Detailed technical contracts/design | FINAL / LOCKED |
| 05 | Agent Behaviour v1.0 | Agent lifecycle and behavior invariants | FINAL / LOCKED |
| 06 | Tool & Permission v1.0 | Capability/authorization model | FINAL / LOCKED |
| 07 | Memory & Context v1.0 | Context/memory contracts and authority | FINAL / LOCKED |
| 08 | Error Recovery v1.0 | Failure/recovery lifecycle | FINAL / LOCKED |
| 09 | Testing & Validation v1.0 | Quality and completion gates | FINAL / LOCKED |
| 10 | Security & Sandbox v1.0 | Security authority and isolation | FINAL / LOCKED |
| 11 | VS Code Integration v1.0 | Primary client integration | FINAL / LOCKED |
| 12 | Project Plan & Progress v1.0 | Implementation control | FINAL / LOCKED |
| 13 | Repository / Module Blueprint | Physical code organization | Planned dependency |
| 14 | Data / Schema Specification | Persistent/runtime data contracts | Planned dependency |
| 15 | API / Protocol Specification | Service/client/tool contracts | Planned dependency |
| 16 | Configuration Specification | Runtime/configuration contracts | Planned dependency |
| 17 | Observability & Audit Specification | Telemetry/audit/reporting | Planned dependency |
| 18 | Deployment / Operations Specification | Build/install/runtime operations | Planned dependency |
| 19 | Release & Maintenance Specification | Release, upgrade and lifecycle | Planned dependency |

# 4. Implementation Dependency Principle

PRD

↓

SRS

↓

Architecture

↓

Technical Design

↓

Behaviour + Tool/Permission + Memory/Context + Security

↓

Data/Protocol/Repository/Configuration contracts

↓

Core Runtime

↓

Validation + Recovery + Observability

↓

VS Code / CLI clients

↓

Integration / E2E

↓

Deployment / Release

The exact ordering of parallel implementation streams may vary, but no stream may violate a higher-level locked dependency or security boundary.

# 5. Master Implementation Phases

| Phase | Name | Primary outcome | Exit gate |
| --- | --- | --- | --- |
| P0 | Foundation & Repository | Buildable repository, tooling, conventions, CI skeleton | Foundation Gate |
| P1 | Core Contracts & State | Models, IDs, schemas, task/session state | Contract Gate |
| P2 | Workspace & Repository Intelligence | Safe workspace binding, map/search/context inputs | Repository Gate |
| P3 | Tool Gateway & Permissions | Typed tools + Policy Engine + authorization | Security Gate A |
| P4 | Execution & Patch Engine | Filesystem/process/patch/Git controlled execution | Execution Gate |
| P5 | Memory & Context | Context providers, ranking, budgets, provenance | Context Gate |
| P6 | Agent Orchestration & Behaviour | Planner/orchestrator/lifecycle | Behaviour Gate |
| P7 | Validation & Error Recovery | Validation Runner, Completion Gate, Recovery Controller | Recovery/Validation Gate |
| P8 | Observability & Audit | Events, evidence, reports, diagnostics | Audit Gate |
| P9 | VS Code Integration | Client protocol/UI/approvals/diff/progress | Client Gate |
| P10 | End-to-End Hardening | Security, regression, reliability, performance | E2E Gate |
| P11 | Deployment & Release | Packaging, install, operations, release candidate | Release Gate |

# 6. Phase P0 — Foundation & Repository

Create canonical repository structure.

Pin language/runtime/tooling versions.

Establish lint/type-check/test configuration.

Create CI skeleton.

Create configuration/environment separation.

Create secure local development workflow.

Add baseline documentation and contribution/change-control files.

Create test fixture framework.

| Entry | Deliverables | Validation | Exit |
| --- | --- | --- | --- |
| Locked 01–12 baselines | Repository skeleton, CI, tooling, config baseline | Clean build + basic test + lint | Foundation reproducible |

# 7. Phase P1 — Core Contracts & State

Define IDs/correlation IDs.

Define Task/Session/Plan/Step state models.

Define ToolRequest/ToolResult.

Define PolicyDecision.

Define ContextItem/MemoryRecord.

Define ErrorRecord/Recovery state.

Define ValidationResult/Completion evidence.

Define event envelope and protocol primitives.

| Entry | Deliverables | Validation | Exit |
| --- | --- | --- | --- |
| P0 PASS | Typed contracts + serialization tests | Unit/contract tests | All core contracts stable |

# 8. Phase P2 — Workspace & Repository Intelligence

Workspace discovery/binding.

Canonical path/scope resolution.

Repository map/index.

File/search/symbol interfaces.

Current-state refresh/invalidation.

Safe repository context extraction.

Repository fixture suite.

| Entry | Deliverables | Validation | Exit |
| --- | --- | --- | --- |
| P1 contracts + Security rules | Workspace manager + repository intelligence | Security path tests + repository tests | Current repository can be safely understood |

# 9. Phase P3 — Tool Gateway & Permissions

Tool registry and schemas.

Tool Gateway.

Policy Engine.

ALLOW/ASK/DENY/RESTRICT decisions.

Approval correlation/expiry.

Scope and risk evaluation.

Security audit events.

Registered initial tool set.

Hard gate: No privileged executor is integrated as an agent capability until this phase passes Security Gate A.

# 10. Phase P4 — Execution & Patch Engine

Workspace/file operations.

Process execution controls.

Patch application.

Diff/scope verification.

Git adapter/checkpoint behavior.

Timeout/cancellation.

Output/artifact capture.

User-change preservation.

| Entry | Validation | Exit |
| --- | --- | --- |
| P3 Security Gate A | Sandbox, path, process, patch, Git and cancellation tests | Controlled execution works without boundary violations |

# 11. Phase P5 — Memory & Context

Context providers.

Context ranking.

Context budget.

Context Manifest.

Memory persistence and isolation.

Freshness/invalidation.

Provenance.

Secret filtering.

Current-evidence precedence.

| Entry | Validation | Exit |
| --- | --- | --- |
| P4 execution + Memory/Context baseline | Context/memory unit, integration and security tests | Safe, bounded, current context available to orchestration |

# 12. Phase P6 — Agent Orchestration & Behaviour

Task lifecycle state machine.

Request understanding.

Planning.

Execution loop.

Tool request generation.

Approval pauses.

Validation transitions.

Completion Gate integration.

Cancellation handling.

Agent Behaviour invariant enforcement.

| Entry | Validation | Exit |
| --- | --- | --- |
| P1–P5 required contracts/services | Behavior tests + controlled E2E workflow | Agent can perform bounded repository task lifecycle |

# 13. Phase P7 — Validation & Error Recovery

Validation Runner.

Gate registry.

Evidence collection.

Error normalization/classification.

Recovery eligibility.

Diagnosis/repair planning.

Bounded retry/attempt budgets.

Repeated-failure detection.

Retest loop.

Completion evidence.

Hard gate: The agent cannot be considered implementation-ready until it can safely fail, recover, retest and stop.

# 14. Phase P8 — Observability & Audit

Structured runtime events.

Task/tool/policy/validation/recovery audit.

Correlation across client/runtime.

Safe diagnostic logs.

Evidence artifact indexing.

Task progress reporting.

Security audit protection.

# 15. Phase P9 — VS Code Integration

Extension activation.

Runtime client/protocol.

Chat interface.

Task/sidebar/status views.

Approval UI.

Diff/editor integration.

Diagnostics.

Progress/cancellation.

Reconnect/resynchronization.

Client security tests.

Boundary rule: VS Code remains a client. It must never become a direct executor or authorization bypass.

# 16. Phase P10 — End-to-End Hardening

Full E2E workflows.

Security attack/bypass suite.

Prompt-injection scenarios.

MCP boundary tests.

Recovery stress/failure injection.

Restart/disconnect/cancellation.

Large repository/context tests.

Performance benchmarks.

Regression suite.

False-completion testing.

# 17. Phase P11 — Deployment & Release

Build/package.

Installation workflow.

Configuration validation.

Runtime startup/shutdown.

Upgrade/migration strategy.

Release notes/changelog.

Security release checklist.

Evidence archive.

Release candidate acceptance.

# 18. Phase Gates

| Gate | Required evidence | Failure result |
| --- | --- | --- |
| Foundation Gate | Build/tooling/CI baseline | Phase remains open |
| Contract Gate | Schema/state contract tests | Phase remains open |
| Repository Gate | Workspace/repository tests | Phase remains open |
| Security Gate A | Tool/policy/sandbox tests | Privileged execution blocked |
| Execution Gate | Execution/patch/Git tests | Agent implementation blocked |
| Context Gate | Memory/context tests | Orchestration context blocked |
| Behaviour Gate | Lifecycle/behavior tests | E2E blocked |
| Recovery/Validation Gate | Recovery + completion tests | Completion blocked |
| Audit Gate | Traceability/event tests | Release evidence incomplete |
| Client Gate | VS Code integration/security tests | Client release blocked |
| E2E Gate | End-to-end/security/reliability tests | Release blocked |
| Release Gate | All mandatory release conditions | Release prohibited |

# 19. Work Item Structure

WorkItem {

id

phase

title

objective

specification_refs[]

dependencies[]

owner

status

risk

files_scope[]

tests_required[]

acceptance_criteria[]

evidence_refs[]

blocker_refs[]

decision_refs[]

created_at

updated_at

}

# 20. Progress State Model

| State | Meaning | Transition |
| --- | --- | --- |
| BACKLOG | Identified, not started | → READY |
| READY | Dependencies satisfied | → IN_PROGRESS |
| IN_PROGRESS | Active implementation | → REVIEW / BLOCKED |
| REVIEW | Implementation awaiting review/tests | → DONE / CHANGES_REQUIRED |
| CHANGES_REQUIRED | Review/validation found issue | → IN_PROGRESS |
| BLOCKED | Cannot proceed due dependency/risk/decision | → READY / IN_PROGRESS |
| DONE | Acceptance + evidence satisfied | Terminal for work item |
| CANCELLED | Work intentionally stopped | Terminal unless re-opened by change control |

# 21. Definition of Ready

Work item has a clear objective.

Applicable locked specification references are known.

Dependencies are satisfied or explicitly planned.

Scope/files are identifiable.

Acceptance criteria are testable.

Required security/permission implications are understood.

Required test strategy is identified.

No unresolved blocker makes immediate execution unsafe.

# 22. Definition of Done

Implementation is complete within declared scope.

Required tests pass.

Security checks pass where applicable.

Actual diff matches intended scope.

Acceptance criteria are satisfied.

Relevant documentation is updated.

Evidence references are recorded.

No unresolved blocking error remains.

Code is in the expected repository state.

Completion does not depend on an unverified assumption.

# 23. Dependency Management

Represent hard dependencies explicitly.

Do not start a blocked work item merely because it appears next in the list.

Parallel work is allowed only when interfaces are stable enough.

Changes to upstream contracts trigger downstream impact review.

Record dependency blockers with an owner and resolution condition.

Never silently replace a dependency with an incompatible shortcut.

# 24. Research → Implementation Workflow

RESEARCH

↓

EXTRACT USEFUL PATTERNS

↓

LICENSE / SECURITY / ARCHITECTURE REVIEW

↓

ADOPT / ADAPT / REJECT DECISION

↓

CREATE INTERNAL CONTRACT

↓

IMPLEMENT

↓

TEST

↓

INTEGRATE

↓

RECORD SOURCE + DECISION

External repositories are references, not authoritative specifications.

Do not copy code blindly.

Record why a pattern was adopted and where it maps into our architecture.

Check license compatibility before integrating source code.

Security-sensitive patterns require additional review.

# 25. Repository Integration Policy

| Decision | Meaning |
| --- | --- |
| ADOPT | Use the pattern/component with minimal adaptation after review. |
| ADAPT | Use the concept but implement against our contracts. |
| WRAP | Keep external implementation behind our internal interface. |
| REPLACE | Use the idea but select another implementation. |
| REJECT | Do not use because it conflicts with architecture/security/scope/license. |

Internal interfaces remain authoritative.

External repository structure does not dictate our architecture.

Every adopted dependency has ownership/version/license/security information.

# 26. Risk Register

| Risk | Impact | Mitigation | Trigger |
| --- | --- | --- | --- |
| Scope creep | High | Locked specs + change control | Unplanned feature request |
| Architecture drift | High | Traceability + gate review | Implementation conflicts with baseline |
| Security bypass | Critical | Defense-in-depth + security tests | Unauthorized side effect |
| False completion | Critical | Completion Gate | Missing/failed evidence |
| Endless recovery | High | Budgets + repetition detection | Repeated failure |
| Context staleness | High | Refresh/invalidation | Repository changed |
| User data loss | Critical | Git/diff/scope controls | Unrelated change overwritten |
| Dependency instability | Medium | Pin/version/test | Build/runtime drift |
| External repo license issue | High | License review | Incompatible terms |
| Performance regression | Medium | Benchmarks | Target exceeded |
| Client/runtime mismatch | High | Versioned protocol | Protocol incompatibility |
| Test flakiness | Medium | Quarantine/root-cause policy | Unstable gate |

# 27. Blocker Management

Every blocker receives a stable ID.

Record affected phase/work items.

Record cause, evidence and resolution condition.

Classify blocker as technical, security, dependency, decision, environment or external.

Security blockers cannot be downgraded to ordinary technical blockers.

Blocked work does not count as completed.

Replanning must preserve locked invariants.

BLOCKED

├── Cause

├── Evidence

├── Impact

├── Resolution condition

├── Owner

└── Next review trigger

# 28. Decision Management

| Decision field | Required content |
| --- | --- |
| Decision ID | Stable identifier |
| Question | What required a decision |
| Options | Meaningful alternatives considered |
| Decision | Selected option |
| Rationale | Evidence/reasoning |
| Impact | Affected docs/modules/phases |
| Reversibility | Easy / Moderate / Hard |
| Approver | If required by governance |
| Date/version | When it became effective |

Decisions affecting locked behavior trigger change control.

Temporary implementation decisions must be labeled temporary.

Rejected alternatives should be recorded for high-impact decisions.

# 29. Change Control

| Change type | Default handling |
| --- | --- |
| Bug fix within locked behavior | Normal implementation + regression test |
| Internal refactor | Normal review if contracts/invariants unchanged |
| New feature in existing scope | Add work item + acceptance/tests |
| Scope expansion | Change request + PRD/SRS impact review |
| Behavior change | Affected specification review + version/change control |
| Security rule change | Security/architecture review |
| Protocol contract change | Protocol versioning + compatibility tests |
| Architecture change | Architecture review + downstream impact |
| Locked document change | Formal change control; new version |

No implementation change may silently redefine a locked requirement.

# 30. Progress Reporting

| Report | Required content | Cadence |
| --- | --- | --- |
| Daily/working status | Completed, in-progress, blocked, next | During active implementation |
| Phase report | Gate status, evidence, risks | At phase boundary |
| Milestone report | Deliverables, deviations, decisions | At milestone |
| Release report | All gates + known issues + evidence | Release candidate |
| Master progress | Overall phase/document/work-item status | Continuous source of truth |

Progress percentages are secondary to gate status.

A phase is not complete because a percentage reaches 100%; its exit criteria must pass.

Blocked items remain visible in progress reporting.

# 31. Master Progress Board

| Phase | Status at baseline | Required evidence | Next action |
| --- | --- | --- | --- |
| P0 Foundation | PLANNED | Foundation Gate | Create implementation repository |
| P1 Contracts | PLANNED | Contract Gate | Implement core models/schemas |
| P2 Repository | PLANNED | Repository Gate | Implement workspace/repository intelligence |
| P3 Tools/Permissions | PLANNED | Security Gate A | Implement Tool Gateway + Policy Engine |
| P4 Execution | PLANNED | Execution Gate | Implement executors/patch/Git |
| P5 Context | PLANNED | Context Gate | Implement Memory & Context |
| P6 Behaviour | PLANNED | Behaviour Gate | Implement orchestration |
| P7 Validation/Recovery | PLANNED | Recovery/Validation Gate | Implement validation + recovery |
| P8 Observability | PLANNED | Audit Gate | Implement events/audit/reporting |
| P9 VS Code | PLANNED | Client Gate | Implement extension/client |
| P10 Hardening | PLANNED | E2E Gate | Run full security/reliability/performance |
| P11 Release | PLANNED | Release Gate | Package and release |

Baseline status is PLANNED because this document establishes the implementation roadmap; actual status must be updated only from implementation evidence.

# 32. Milestones

| Milestone | Completion condition |
| --- | --- |
| M0 — Repository Ready | P0 exit gate PASS |
| M1 — Runtime Contracts Ready | P1 exit gate PASS |
| M2 — Repository Understanding Ready | P2 exit gate PASS |
| M3 — Secure Tooling Ready | P3 security gate PASS |
| M4 — Controlled Execution Ready | P4 gate PASS |
| M5 — Context Ready | P5 gate PASS |
| M6 — Agent Core Ready | P6 gate PASS |
| M7 — Safe Self-Recovery Ready | P7 gate PASS |
| M8 — Observable Runtime Ready | P8 gate PASS |
| M9 — VS Code Alpha | P9 gate PASS |
| M10 — Hardened Candidate | P10 gate PASS |
| M11 — Release Candidate | P11 gate PASS |

# 33. Minimum Viable Implementation Order

1. Repository + CI foundation

2. Core typed contracts

3. Workspace/scope/security primitives

4. Tool Gateway + Policy Engine

5. Safe filesystem/process/patch execution

6. Repository intelligence

7. Memory/context

8. Agent orchestration

9. Validation + Completion Gate

10. Error Recovery

11. Observability/audit

12. VS Code integration

13. E2E/security/reliability hardening

14. Deployment/release

This order prioritizes the security and control plane before broad autonomous execution.

# 34. First Implementation Sprint Definition

Initialize repository and canonical directory structure.

Set Python/runtime/tool versions.

Create lint/type-check/test/CI baseline.

Implement core ID/event/config primitives.

Create initial unit-test harness.

Create security test fixture harness.

Create initial ToolDefinition/ToolRequest/PolicyDecision contracts.

Create project progress tracker using this document's work-item model.

Do not enable unrestricted process execution during the foundation sprint.

Sprint exit: Buildable, testable repository with the initial contract/security skeleton—not a partially autonomous agent.

# 35. Progress Evidence Model

ProgressEvidence {

work_item_id

phase_id

status

commit_or_revision

tests_passed[]

security_checks[]

acceptance_results[]

artifact_refs[]

diff_scope

blockers[]

decisions[]

recorded_at

}

Evidence must correspond to the actual repository state.

Later changes can invalidate earlier evidence.

Evidence should be reproducible where practical.

# 36. Project Metrics

| Metric | Meaning |
| --- | --- |
| Phase completion | Phases passing exit gates / total phases |
| Work item completion | DONE items / total planned items |
| Blocked work | BLOCKED items + age |
| Requirement coverage | Requirements mapped to implementation/tests |
| Security gate pass | Mandatory security gate status |
| Regression pass | Critical regression status |
| False completion | Count of invalid completion claims; target zero |
| Recovery success | Recovered failures / eligible failures |
| Test stability | Flaky/unstable test rate |
| Change churn | Reopened/reworked work items |
| Architecture deviations | Approved deviations from baseline |

Metrics are management signals and do not override hard acceptance or security gates.

# 37. Release Readiness Checklist

All required phases have passed their exit gates.

All mandatory security tests pass.

All critical regression tests pass.

Completion Gate behavior is verified.

Recovery budgets/repetition detection are verified.

VS Code client boundary is verified.

Documentation is version-aligned.

Known blockers are zero or formally dispositioned.

Release artifacts are reproducible and traceable.

Change log/release notes are prepared.

Security-sensitive changes have required review.

Evidence archive is complete.

# 38. Project Governance Invariants

PPP1: Locked specifications are not silently changed during implementation.

PPP2: A blocked item is not DONE.

PPP3: A phase cannot close without its exit gate.

PPP4: Security gates cannot be skipped for schedule reasons.

PPP5: Progress claims require evidence.

PPP6: Dependencies are explicit.

PPP7: Scope expansion requires change control.

PPP8: External repositories are reviewed before adoption.

PPP9: User-impacting changes remain traceable.

PPP10: Current repository state determines implementation evidence.

PPP11: Earlier PASS evidence may be invalidated by later changes.

PPP12: Completion requires validation evidence, not code existence.

PPP13: Critical security violations block release.

PPP14: Project replanning cannot weaken locked security/behavior invariants.

PPP15: Every implementation stream has a known next actionable state.

# 39. Acceptance Criteria

| ID | Area | Acceptance condition |
| --- | --- | --- |
| PPP-A01 | Baseline | Locked document set is represented and traceable. |
| PPP-A02 | Phases | Implementation phases have dependencies, deliverables and gates. |
| PPP-A03 | Work items | Work-item structure supports evidence-based status. |
| PPP-A04 | Ready/Done | Definition of Ready and Done are explicit. |
| PPP-A05 | Security | Security gates precede unrestricted execution. |
| PPP-A06 | Validation | Validation/Completion gates control completion. |
| PPP-A07 | Recovery | Recovery is included as a required implementation capability. |
| PPP-A08 | Research | External repo adoption has review/adaptation policy. |
| PPP-A09 | Risks | Critical project risks have mitigations. |
| PPP-A10 | Blockers | Blockers are explicit and cannot masquerade as progress. |
| PPP-A11 | Decisions | High-impact decisions are traceable. |
| PPP-A12 | Progress | Master progress board exists. |
| PPP-A13 | Evidence | Implementation progress maps to repository state/evidence. |
| PPP-A14 | Release | Release readiness conditions are explicit. |
| PPP-A15 | Change control | Baseline-changing work follows formal change control. |

# 40. Traceability to Locked Baselines

| Baseline | Project-plan impact |
| --- | --- |
| 01 PRD v1.0 | Scope, product goals and success criteria. |
| 02 SRS v1.0 | Requirement implementation and acceptance. |
| 03 System Architecture v1.0 | Phase/component dependencies. |
| 04 Technical Design v1.0 | Module implementation sequence. |
| 05 Agent Behaviour v1.0 | Behavior gate and invariants. |
| 06 Tool & Permission v1.0 | Security-first tool-control phase. |
| 07 Memory & Context v1.0 | Context implementation and gate. |
| 08 Error Recovery v1.0 | Recovery implementation and gate. |
| 09 Testing & Validation v1.0 | Mandatory validation/completion gates. |
| 10 Security & Sandbox v1.0 | Security-first execution boundary. |
| 11 VS Code Integration v1.0 | Client integration phase and gate. |

# 41. Implementation Mapping

| Planning artifact | Expected repository location |
| --- | --- |
| Master plan | docs/project/PROJECT_PLAN_PROGRESS.md |
| Work items | docs/project/work-items/ or tracker |
| Phase reports | docs/project/phases/ |
| Decision log | docs/project/decisions/ |
| Risk register | docs/project/RISK_REGISTER.md |
| Change log | docs/project/CHANGELOG.md |
| Progress evidence | artifacts/project-progress/ |
| Test evidence | artifacts/test-results/ |
| Release evidence | artifacts/release/ |
| CI | .github/workflows/ |

Exact paths may evolve with the Repository/Module Blueprint. The governance model and phase gates remain locked.

# 42. Change Control

Changing phase order requires dependency-impact review.

Adding a phase requires updated milestones and traceability.

Changing an exit gate requires validation review.

Changing security-first sequencing requires security/architecture review.

Changing the Definition of Done affects every future work item and requires project-level approval.

New external repository adoption requires source/license/security decision record.

Any change to this locked baseline creates a new version; v1.0 remains immutable as historical baseline.

# 43. Final Status

STATUS: FINAL / LOCKED — v1.0

This Project Plan & Progress Specification v1.0 is the authoritative implementation-control baseline for the AI Software Co-Agent. It defines the 19-document baseline, implementation phases P0–P11, dependencies, gates, work-item lifecycle, Definition of Ready/Done, research-to-implementation process, risks, blockers, decisions, progress evidence, milestones, release readiness and governance invariants.

— END OF PROJECT PLAN & PROGRESS SPECIFICATION v1.0 —