AI SOFTWARE CO-AGENT

TASK BACKLOG

Version 1.0 — FINAL / LOCKED

Document ID: TBL-001 • Implementation-ready work-item baseline

| Field | Value |
| --- | --- |
| Document | Task Backlog |
| Version | v1.0 |
| Status | FINAL / LOCKED |
| Product | AI Software Co-Agent |
| Purpose | Convert the locked architecture and implementation plan into an ordered, traceable backlog of implementation, testing, security, documentation and release work. |
| Authority | Task sequencing and dependencies are governed here; detailed behavior remains governed by the applicable locked specifications. |
| Change policy | Material scope, dependency, priority or acceptance changes require versioned backlog/change control. |

Lock Statement: Task Backlog v1.0 is the canonical implementation backlog baseline. Tasks may be broken into smaller implementation tickets without changing their locked intent, dependencies or acceptance conditions.

# 1. Backlog Mission

The backlog turns the approved architecture into executable work. It prioritizes safety-critical foundations before autonomy, keeps work traceable to locked documents, and makes each task independently reviewable through explicit acceptance criteria and evidence.

Backlog principle: No task is considered Done because code exists; it is Done only when its required evidence and acceptance criteria pass.

# 2. Backlog Status Model

| Status | Meaning |
| --- | --- |
| BACKLOG | Approved work not yet started. |
| READY | Dependencies satisfied and implementation can begin. |
| IN PROGRESS | Active implementation. |
| BLOCKED | Dependency, decision or gate prevents progress. |
| READY FOR REVIEW | Implementation and required tests complete. |
| GATE REVIEW | Evidence is being checked against the phase gate. |
| DONE | Acceptance criteria and required evidence passed. |
| DEFERRED | Intentionally moved outside current implementation scope. |
| REJECTED | Explicitly removed by approved decision/change control. |

# 3. Priority Model

| Priority | Meaning |
| --- | --- |
| P0 | Critical foundation/security/release blocker. |
| P1 | Required for core usable system. |
| P2 | Important capability or quality improvement. |
| P3 | Optional enhancement; not required for v1 core. |

# 4. Work Item Types

| Type | Use |
| --- | --- |
| EPIC | Major implementation area containing related tasks. |
| TASK | Concrete implementation work. |
| SPIKE | Time-bounded investigation/benchmark producing evidence. |
| TEST | Dedicated validation/security/reliability work. |
| DOC | Documentation/traceability work. |
| OPS | Build/CI/release/operational work. |
| ADR | Formal architecture/technology decision work. |

# 5. Master Backlog Structure

EPIC-01 Foundation

EPIC-02 Core Contracts & State

EPIC-03 Security & Workspace

EPIC-04 Tools, Policy & Approval

EPIC-05 Controlled Execution

EPIC-06 Repository Intelligence

EPIC-07 Context & Memory

EPIC-08 Model Gateway & Agent

EPIC-09 Validation, Completion & Recovery

EPIC-10 Audit, Artifacts & Observability

EPIC-11 VS Code & CLI

EPIC-12 E2E, Security & Performance

EPIC-13 Release

EPIC-14 Deferred Technology / Research

# 6. Epic Summary

| Epic | Outcome | Priority | Phase |
| --- | --- | --- | --- |
| EPIC-01 | Reproducible repository/tooling baseline | P0 | P0 |
| EPIC-02 | Stable types, state and protocol | P0 | P1 |
| EPIC-03 | Safe scope and security primitives | P0 | P2 |
| EPIC-04 | Single capability authorization path | P0 | P3 |
| EPIC-05 | Bounded real-world execution | P0 | P4 |
| EPIC-06 | Repository understanding | P1 | P5 |
| EPIC-07 | Scoped context and memory | P1 | P5 |
| EPIC-08 | Controlled model-driven agent | P1 | P6 |
| EPIC-09 | Evidence-based completion and recovery | P0 | P7 |
| EPIC-10 | Traceability and evidence | P1 | P8 |
| EPIC-11 | Developer clients | P1 | P9 |
| EPIC-12 | Hardening | P0 | P10 |
| EPIC-13 | Release package | P0 | P11 |
| EPIC-14 | Deferred evidence-driven choices | P2/P3 | As triggered |

# 7. EPIC-01 — Foundation Backlog

| ID | Type | Task | Pri | Depends | Acceptance |
| --- | --- | --- | --- | --- | --- |
| T001 | TASK | Create canonical repository tree from Repository Blueprint. | P0 | — | Required root/module structure exists. |
| T002 | TASK | Create Python package/build configuration. | P0 | T001 | Clean environment installs/builds successfully. |
| T003 | TASK | Create test, scripts, configs and docs skeleton. | P0 | T001 | Expected directories and baseline files exist. |
| T004 | OPS | Create CI smoke workflow. | P0 | T002,T003 | CI installs and runs baseline checks. |
| T005 | OPS | Add lint/format baseline. | P1 | T002 | Quality command runs reproducibly. |
| T006 | OPS | Add static type-check baseline. | P1 | T002 | Canonical type checker runs without configuration drift. |
| T007 | OPS | Add dependency/security scanning. | P0 | T004 | CI performs required scans. |
| T008 | OPS | Add secret/config safety checks. | P0 | T003 | Secrets are not accepted in source-controlled config. |
| T009 | DOC | Record bootstrap/run instructions. | P1 | T001–T004 | New developer can reproduce baseline setup. |
| T010 | GATE | Pass G0 Foundation Gate. | P0 | T001–T009 | G0 evidence package approved. |

# 8. EPIC-02 — Core Contracts & State

| ID | Type | Task | Pri | Depends | Acceptance |
| --- | --- | --- | --- | --- | --- |
| T011 | TASK | Implement stable IDs/correlation identifiers. | P0 | T002 | Session/task/request/event IDs are generated and propagated. |
| T012 | TASK | Implement common result/error/event types. | P0 | T011 | Typed contracts cover success/failure/event envelopes. |
| T013 | TASK | Implement session state model. | P0 | T011,T012 | Session lifecycle transitions are tested. |
| T014 | TASK | Implement task state machine. | P0 | T013 | Invalid transitions are rejected. |
| T015 | TASK | Implement versioned client/runtime protocol. | P0 | T012 | Messages validate and version correctly. |
| T016 | TASK | Implement protocol error envelopes. | P1 | T015 | Malformed/unsupported requests produce typed errors. |
| T017 | TEST | Create contract/serialization test suite. | P0 | T015,T016 | Contract tests pass. |
| T018 | TEST | Create state-transition test suite. | P0 | T014 | Valid/invalid transitions pass. |
| T019 | TASK | Implement minimal runtime health/task command. | P1 | T014,T015 | Runtime accepts a safe task command. |
| T020 | GATE | Pass G1 Contracts Gate. | P0 | T011–T019 | G1 evidence package approved. |

# 9. EPIC-03 — Security & Workspace

| ID | Type | Task | Pri | Depends | Acceptance |
| --- | --- | --- | --- | --- | --- |
| T021 | TASK | Implement canonical workspace identity/scope. | P0 | T014 | Task scope is explicit. |
| T022 | TASK | Implement canonical path resolution. | P0 | T021 | Paths resolve deterministically. |
| T023 | TASK | Implement traversal/symlink escape protection. | P0 | T022 | Out-of-scope access is blocked. |
| T024 | TASK | Implement protected-path policy. | P0 | T022 | Protected targets require correct policy outcome. |
| T025 | TASK | Implement resource/time/concurrency limits. | P0 | T014 | Limits are enforced. |
| T026 | TASK | Implement secret filtering/redaction primitives. | P0 | T012 | Known secret patterns are filtered from outputs/events. |
| T027 | TASK | Implement sandbox interface. | P0 | T025 | Executors can require sandbox guarantees. |
| T028 | TEST | Build security boundary/adversarial fixtures. | P0 | T021–T027 | Fixtures cover escape/bypass cases. |
| T029 | TEST | Run fail-closed security-control tests. | P0 | T025–T027 | Affected privileged actions block on control failure. |
| T030 | GATE | Pass G2 Security/Scope Gate. | P0 | T021–T029 | G2 evidence package approved. |

# 10. EPIC-04 — Tools, Policy & Approval

| ID | Type | Task | Pri | Depends | Acceptance |
| --- | --- | --- | --- | --- | --- |
| T031 | TASK | Define canonical ToolRequest/ToolResult contracts. | P0 | T012,T015 | Typed tool contracts validate. |
| T032 | TASK | Implement Tool Registry. | P0 | T031 | Capabilities are explicitly registered. |
| T033 | TASK | Implement Tool Gateway. | P0 | T031,T032 | All registered tool calls route through gateway. |
| T034 | TASK | Implement PolicyRequest/PolicyDecision. | P0 | T031,T033 | Policy produces ALLOW/ASK/DENY/RESTRICT. |
| T035 | TASK | Implement approval lifecycle. | P0 | T034,T015 | ASK requests are explicit and correlated. |
| T036 | TASK | Implement policy scope/risk evaluation. | P0 | T021,T025,T034 | Target/risk/scope influence decision. |
| T037 | TEST | Build policy decision matrix tests. | P0 | T034–T036 | Expected decisions pass. |
| T038 | TEST | Build tool/policy bypass tests. | P0 | T033–T036 | Alternate authorization paths fail. |
| T039 | TASK | Implement audit hook for material tool decisions. | P1 | T033,T034 | Decision is traceable. |
| T040 | GATE | Pass G3 Capability Control Gate. | P0 | T031–T039 | G3 evidence package approved. |

# 11. EPIC-05 — Controlled Execution

| ID | Type | Task | Pri | Depends | Acceptance |
| --- | --- | --- | --- | --- | --- |
| T041 | TASK | Implement scoped filesystem executor. | P0 | T033,T036,T027 | Authorized file operations work; escapes fail. |
| T042 | TASK | Implement bounded process executor. | P0 | T033,T036,T027 | Timeout/resource/cancellation controls work. |
| T043 | TASK | Implement patch/change engine. | P0 | T041 | Patch conflicts are detected. |
| T044 | TASK | Implement user-change protection. | P0 | T041,T043 | Unrelated user edits are preserved. |
| T045 | TASK | Implement Git adapter. | P1 | T033,T036,T043 | Git operations use controlled capability path. |
| T046 | TASK | Implement cancellation propagation. | P0 | T042,T014 | Cancellation stops affected work. |
| T047 | TEST | Execution integration/security tests. | P0 | T041–T046 | Representative execution suite passes. |
| T048 | TEST | Process/resource abuse tests. | P0 | T042 | Excessive runtime/output/concurrency is bounded. |
| T049 | GATE | Pass G4 Execution Gate. | P0 | T041–T048 | G4 evidence package approved. |

# 12. EPIC-06 — Repository Intelligence

| ID | Type | Task | Pri | Depends | Acceptance |
| --- | --- | --- | --- | --- | --- |
| T050 | TASK | Implement repository root/discovery service. | P1 | T021,T041 | Repository scope is identified safely. |
| T051 | TASK | Implement file/content search adapter. | P1 | T041 | Search respects scope. |
| T052 | TASK | Implement repository map/index abstraction. | P1 | T050,T051 | Relevant repository structure can be represented. |
| T053 | TASK | Implement symbol intelligence interface. | P2 | T052 | Symbol provider contract exists. |
| T054 | TEST | Repository intelligence scope tests. | P1 | T050–T053 | No out-of-scope repository access. |
| T055 | TEST | Representative repository benchmark. | P1 | T052,T053 | Baseline relevance/performance evidence recorded. |

# 13. EPIC-07 — Context & Memory

| ID | Type | Task | Pri | Depends | Acceptance |
| --- | --- | --- | --- | --- | --- |
| T056 | TASK | Implement ContextProvider interface. | P1 | T012,T052 | Providers return typed context items. |
| T057 | TASK | Implement context ranking/filtering. | P1 | T056 | Relevant items rank within budget. |
| T058 | TASK | Implement context budget manager. | P0 | T057 | Unbounded context is prevented. |
| T059 | TASK | Implement Context Manifest/provenance. | P1 | T057 | Context source/freshness metadata is available. |
| T060 | TASK | Implement MemoryStore interface. | P1 | T012 | Memory persistence is abstracted. |
| T061 | TASK | Implement scoped memory manager. | P1 | T060,T021 | Memory is task/project scoped. |
| T062 | TASK | Implement stale-memory handling. | P1 | T061,T059 | Current repository state can outrank stale memory. |
| T063 | TEST | Context/memory security tests. | P0 | T056–T062 | Memory cannot authorize and secrets are filtered. |
| T064 | TEST | Context relevance/budget benchmark. | P1 | T057,T058 | Representative tasks fit context budget. |
| T065 | GATE | Pass G5 Context Gate. | P1 | T056–T064 | G5 evidence package approved. |

# 14. EPIC-08 — Model Gateway & Agent

| ID | Type | Task | Pri | Depends | Acceptance |
| --- | --- | --- | --- | --- | --- |
| T066 | TASK | Implement ModelGateway interface. | P1 | T012 | Provider is replaceable. |
| T067 | TASK | Implement model adapter contract/conformance tests. | P1 | T066 | Provider adapter conforms. |
| T068 | TASK | Implement planner interface. | P1 | T056,T066 | Planner consumes controlled context. |
| T069 | TASK | Implement agent behavior state loop. | P1 | T014,T033,T068 | Agent lifecycle is explicit. |
| T070 | TASK | Implement task/tool/recovery budgets. | P0 | T025,T069 | Loops are bounded. |
| T071 | TASK | Implement observation/result incorporation. | P1 | T069,T056 | Tool results refresh task context. |
| T072 | TEST | Agent tool-use behavior suite. | P0 | T069–T071 | No direct executor bypass. |
| T073 | TEST | Model failure/cancellation tests. | P0 | T066,T069,T070 | Failures stop safely. |
| T074 | SPIKE | Benchmark candidate model/provider options. | P2 | T066 | Evidence covers quality/cost/latency/security. |
| T075 | GATE | Pass G6 Agent Gate. | P1 | T066–T074 | G6 evidence package approved. |

# 15. EPIC-09 — Validation, Completion & Recovery

| ID | Type | Task | Pri | Depends | Acceptance |
| --- | --- | --- | --- | --- | --- |
| T076 | TASK | Implement Validation Runner. | P0 | T041,T069 | Checks can be executed through controlled tools. |
| T077 | TASK | Implement validation evidence model. | P0 | T012,T076 | Results are structured and traceable. |
| T078 | TASK | Implement Completion Gate. | P0 | T077 | Only required evidence can establish COMPLETE. |
| T079 | TASK | Implement failure classifier. | P0 | T077 | Failures receive bounded categories. |
| T080 | TASK | Implement Recovery Controller. | P0 | T033,T079 | Recovery actions use normal policy path. |
| T081 | TASK | Implement recovery budgets/retry limits. | P0 | T025,T080 | Repeated failures stop. |
| T082 | TASK | Implement retest workflow. | P0 | T076,T080 | Repair is followed by validation. |
| T083 | TEST | False-completion adversarial suite. | P0 | T078 | Missing/invalid evidence cannot complete. |
| T084 | TEST | Recovery failure/loop suite. | P0 | T080–T082 | Recovery stops safely on exhaustion. |
| T085 | TEST | End-to-end coding task validation. | P0 | T069,T076,T078,T082 | Representative task passes with evidence. |
| T086 | GATE | Pass G7 Quality Gate. | P0 | T076–T085 | G7 evidence package approved. |

# 16. EPIC-10 — Audit, Artifacts & Observability

| ID | Type | Task | Pri | Depends | Acceptance |
| --- | --- | --- | --- | --- | --- |
| T087 | TASK | Implement structured event envelope. | P1 | T012 | Events carry correlation metadata. |
| T088 | TASK | Implement audit recorder. | P0 | T087,T039 | Material actions are recorded. |
| T089 | TASK | Implement artifact store/reference model. | P1 | T012,T077 | Large evidence is referenced safely. |
| T090 | TASK | Implement output redaction layer. | P0 | T026,T087 | Sensitive output is filtered. |
| T091 | TASK | Implement task trace/reconstruction view. | P1 | T088,T089 | Representative task can be reconstructed. |
| T092 | TEST | Audit completeness/correlation tests. | P1 | T087–T091 | Event chains remain correlated. |
| T093 | TEST | Secret leakage tests. | P0 | T090 | Known secrets do not appear in ordinary evidence. |
| T094 | GATE | Pass G8 Evidence Gate. | P1 | T087–T093 | G8 evidence package approved. |

# 17. EPIC-11 — VS Code & CLI

| ID | Type | Task | Pri | Depends | Acceptance |
| --- | --- | --- | --- | --- | --- |
| T095 | TASK | Implement CLI runtime client. | P1 | T015,T019 | CLI uses protocol only. |
| T096 | TASK | Implement VS Code extension shell. | P1 | T015 | Extension connects to runtime. |
| T097 | TASK | Implement chat/task UI. | P1 | T096 | User can submit and monitor tasks. |
| T098 | TASK | Implement approval UI. | P1 | T035,T096 | Approval responses map to exact requests. |
| T099 | TASK | Implement diff/change presentation. | P1 | T043,T096 | Changes are reviewable. |
| T100 | TASK | Implement diagnostics/progress/status. | P1 | T087,T096 | Runtime state is visible. |
| T101 | TASK | Implement reconnect/state synchronization. | P1 | T015,T013,T096 | Client reconnect does not duplicate side effects. |
| T102 | TEST | Client protocol compatibility suite. | P0 | T095–T101 | CLI and VS Code interoperate with same runtime. |
| T103 | TEST | Client bypass/security tests. | P0 | T095–T101 | Clients cannot bypass runtime/policy. |
| T104 | GATE | Pass G9 Client Gate. | P1 | T095–T103 | G9 evidence package approved. |

# 18. EPIC-12 — E2E, Security & Performance

| ID | Type | Task | Pri | Depends | Acceptance |
| --- | --- | --- | --- | --- | --- |
| T105 | TEST | Run complete architecture decision test suite. | P0 | T104 | Applicable ADM tests pass. |
| T106 | TEST | Run injection/untrusted-content suite. | P0 | T069,T103 | Repository/MCP/memory content cannot gain authority. |
| T107 | TEST | Run workspace/process escape suite. | P0 | T041,T042 | Escape/resource attacks are blocked. |
| T108 | TEST | Run MCP policy-boundary suite. | P0 | T033,T067 | MCP cannot bypass internal policy. |
| T109 | TEST | Run user-change protection suite. | P0 | T044 | Unrelated changes remain safe. |
| T110 | TEST | Run failure-injection/recovery suite. | P0 | T080–T082 | Failures recover or stop within budgets. |
| T111 | TEST | Run representative repository E2E suite. | P0 | T085,T104 | Core coding workflows succeed. |
| T112 | TEST | Run performance/resource benchmark suite. | P1 | T064,T074 | Baseline metrics are recorded. |
| T113 | TEST | Run dependency/license/security review. | P0 | T007,T074 | Release dependencies approved. |
| T114 | GATE | Pass G10 Hardening Gate. | P0 | T105–T113 | Release-candidate evidence approved. |

# 19. EPIC-13 — Release

| ID | Type | Task | Pri | Depends | Acceptance |
| --- | --- | --- | --- | --- | --- |
| T115 | OPS | Create reproducible release build. | P0 | T114 | Clean environment produces release artifact. |
| T116 | OPS | Verify package/install/startup workflow. | P0 | T115 | Fresh install passes smoke test. |
| T117 | DOC | Finalize user/developer/security documentation. | P0 | T114 | Documentation matches implementation. |
| T118 | OPS | Create rollback/recovery procedure. | P0 | T115 | Known-good rollback is documented/tested. |
| T119 | DOC | Generate release notes and traceability report. | P1 | T114 | Changes map to backlog/specs. |
| T120 | GATE | Pass G11 Release Gate. | P0 | T115–T119 | Release approval recorded. |

# 20. EPIC-14 — Deferred Technology / Research

| ID | Type | Task | Pri | Trigger | Acceptance |
| --- | --- | --- | --- | --- | --- |
| T121 | SPIKE | Evaluate specific LLM/provider candidates. | P2 | Need/provider benchmark | Decision backed by quality/cost/latency/security evidence. |
| T122 | SPIKE | Evaluate vector/embedding retrieval. | P2 | Context benchmark gap | Adopt only if material measured benefit. |
| T123 | SPIKE | Evaluate container sandbox backend. | P1 | Deployment/security need | Isolation/resource evidence passes. |
| T124 | SPIKE | Evaluate telemetry backend. | P3 | Operational need | Privacy/value review passes. |
| T125 | SPIKE | Evaluate multi-agent framework. | P3 | Measured coordination need | Benefit + isolation + budget evidence. |
| T126 | SPIKE | Evaluate remote database/runtime. | P3 | Scale/deployment trigger | Architecture compatibility proven. |
| T127 | ADR | Record approved deferred technology decision. | P1 | After evidence | ADR and affected docs updated. |

# 21. Cross-Cutting Backlog

| ID | Work | Priority | Rule |
| --- | --- | --- | --- |
| X001 | Maintain traceability from task → spec → architecture decision. | P0 | Required for material work. |
| X002 | Maintain security regression suite. | P0 | Security regressions block release. |
| X003 | Maintain architecture drift checks. | P0 | No alternate authority path. |
| X004 | Maintain dependency/license inventory. | P0 | Required for production dependencies. |
| X005 | Maintain test fixtures for adversarial repositories. | P1 | Use controlled, reproducible fixtures. |
| X006 | Maintain evidence/artifact retention rules. | P1 | No uncontrolled sensitive output. |
| X007 | Update progress/evidence after each gate. | P0 | Gate status must be reconstructable. |
| X008 | Review deferred decisions before release when triggered. | P1 | No hidden unresolved dependency. |

# 22. Dependency Graph

T001–T010 Foundation

↓

T011–T020 Contracts/State

↓

T021–T030 Security/Scope

↓

T031–T040 Tools/Policy

↓

T041–T049 Execution

↓

T050–T065 Repository/Context/Memory

↓

T066–T075 Model/Agent

↓

T076–T086 Validation/Recovery

↓

T087–T094 Evidence

↓

T095–T104 Clients

↓

T105–T114 Hardening

↓

T115–T120 Release

# 23. Critical Path Tasks

| Critical ID | Why critical |
| --- | --- |
| T002 | Build/install foundation. |
| T014 | Authoritative task lifecycle. |
| T021–T023 | Safe workspace boundary. |
| T033–T036 | Single tool authorization path. |
| T041–T042 | Controlled side effects. |
| T058 | Context resource control. |
| T069–T070 | Bounded agent lifecycle. |
| T078 | Authoritative completion. |
| T080–T082 | Bounded recovery. |
| T085 | Representative E2E proof. |
| T105–T114 | Release-blocking hardening. |
| T120 | Final release gate. |

# 24. Parallelizable Work

Security test fixture development may run alongside security implementation.

Protocol contract tests may run alongside state implementation.

VS Code UI prototyping may run alongside runtime development, provided it cannot define authority.

Repository-intelligence benchmarks may run alongside execution work.

Dependency/license review may run in parallel with module implementation.

Performance harness development may precede final performance measurements.

Documentation updates may proceed continuously without altering locked specifications.

# 25. Task-Level Definition of Ready

Task has a unique ID and clear scope.

Applicable specification/baseline is identified.

Dependencies are known.

Acceptance criteria are testable.

Security impact is identified.

Expected repository location is known.

Required evidence is identified.

No unresolved architecture contradiction blocks implementation.

# 26. Task-Level Definition of Done

Implementation is in the correct repository module.

Applicable contracts/specifications are satisfied.

Required automated tests pass.

Security tests pass where applicable.

Errors/cancellation follow the recovery model.

Audit/evidence behavior is implemented where required.

No locked invariant is violated.

Documentation/traceability is updated.

Review is complete.

Acceptance evidence is recorded.

# 27. Security-Critical Task Rules

Security-critical tasks are P0.

Security tests are release-blocking.

Security-control failure must fail closed for affected privileged operations.

Security fixes cannot be replaced by model prompts or documentation.

Policy, sandbox, secret and scope changes require explicit review.

Security bypass findings must create a tracked remediation task.

# 28. Bug / Defect Workflow

DEFECT

↓

CLASSIFY: SECURITY / CORRECTNESS / RELIABILITY / UX / PERFORMANCE

↓

SEVERITY + PRIORITY

↓

ROOT-CAUSE TASK

↓

FIX

↓

REGRESSION TEST

↓

RE-GATE IF AFFECTED

↓

CLOSE WITH EVIDENCE

# 29. Backlog Change Control

| Change | Rule |
| --- | --- |
| Split task | Allowed if intent, acceptance and traceability are preserved. |
| Reorder task | Allowed only when dependency/gate safety is preserved. |
| Change acceptance | Requires review of affected specification and tests. |
| Change priority | Requires impact/gate review. |
| Add new core capability | Requires scope/architecture/security review. |
| Remove mandatory task | Requires explicit change control. |
| Change locked invariant | Not allowed through normal backlog edit; requires new versioned decision. |
| Defer release blocker | Requires formal approval; security/release gates cannot be silently skipped. |

# 30. Backlog Metrics

| Metric | Purpose |
| --- | --- |
| Ready → Done lead time | Delivery flow. |
| Blocked time | Dependency health. |
| Rework rate | Implementation quality. |
| Gate pass rate | Release readiness. |
| Security defect escape | Security quality. |
| False-completion rate | Agent correctness. |
| Recovery success rate | Resilience. |
| Test pass rate | Regression health. |
| Architecture drift findings | Design integrity. |
| Deferred decision count | Technology uncertainty. |

# 31. Progress Reporting Format

PHASE: Pn

GATE: Gn

STATUS: NOT STARTED / IN PROGRESS / BLOCKED / REVIEW / DONE

COMPLETED: <task IDs>

IN PROGRESS: <task IDs>

BLOCKED: <task IDs + reason>

TESTS: <result>

SECURITY: <result>

EVIDENCE: <artifact references>

RISKS: <active risks>

NEXT: <task IDs>

# 32. Release-Blocking Backlog Items

T007 dependency/security scanning

T008 secret/config safety

T023 workspace escape protection

T029 fail-closed security tests

T033 Tool Gateway

T034–T036 Policy/approval/scope controls

T042 process limits

T044 user-change protection

T078 Completion Gate

T081 recovery limits

T083 false-completion tests

T093 secret leakage tests

T103 client bypass tests

T105–T110 adversarial hardening

T113 dependency/license/security review

T120 release gate

# 33. Backlog Invariants

BL1: Every implementation task has a unique stable ID.

BL2: Every material task maps to a locked baseline.

BL3: Dependencies cannot be silently bypassed.

BL4: Security-critical work is release-blocking.

BL5: Tool side-effect work requires the Tool Gateway/Policy path.

BL6: Agent tasks cannot create direct executor paths.

BL7: Completion work requires validation evidence.

BL8: Recovery work cannot weaken policy/security.

BL9: Client tasks cannot create privileged runtime authority.

BL10: Deferred technology is not a hidden prerequisite.

BL11: Every gate has evidence.

BL12: Done means acceptance criteria passed.

BL13: Architecture drift creates remediation/change work.

BL14: User-change protection remains active throughout implementation.

BL15: Release requires full mandatory backlog/gate evidence.

# 34. Acceptance Criteria

| ID | Area | Acceptance condition |
| --- | --- | --- |
| BL-A01 | Coverage | All major implementation areas are represented. |
| BL-A02 | Sequence | Backlog follows dependency-aware implementation order. |
| BL-A03 | Security | Security/scope work precedes privileged execution. |
| BL-A04 | Tools | Single Tool Gateway/Policy implementation is explicit. |
| BL-A05 | Execution | Filesystem/process/patch/Git work is represented. |
| BL-A06 | Context | Repository/context/memory work is represented. |
| BL-A07 | Agent | Model/agent work is bounded and testable. |
| BL-A08 | Quality | Validation/completion/recovery work is explicit. |
| BL-A09 | Evidence | Audit/artifact/observability work is explicit. |
| BL-A10 | Clients | VS Code/CLI work uses same runtime. |
| BL-A11 | Hardening | E2E/security/performance work is release-blocking. |
| BL-A12 | Release | Release tasks and gate are explicit. |
| BL-A13 | Deferred | Deferred technology work is trigger/evidence based. |
| BL-A14 | Traceability | Tasks map to locked documents. |
| BL-A15 | Governance | Change, DoR, DoD and progress rules are defined. |

# 35. Traceability to Locked Baselines

| Baseline | Task Backlog role |
| --- | --- |
| 01 PRD v1.0 | Provides product scope/outcomes represented by epics. |
| 02 SRS v1.0 | Provides requirements mapped to implementation and tests. |
| 03 System Architecture v1.0 | Provides phase/component dependency order. |
| 04 Technical Design v1.0 | Provides module-level implementation tasks. |
| 05 Agent Behaviour v1.0 | Drives agent lifecycle and behavior tasks. |
| 06 Tool & Permission v1.0 | Drives Tool Gateway, Policy and approval tasks. |
| 07 Memory & Context v1.0 | Drives repository/context/memory tasks. |
| 08 Error Recovery v1.0 | Drives recovery, cancellation and failure tasks. |
| 09 Testing & Validation v1.0 | Drives validation, completion and quality gates. |
| 10 Security & Sandbox v1.0 | Drives security, scope, sandbox and adversarial tasks. |
| 11 VS Code Integration v1.0 | Drives client/protocol/UI tasks. |
| 12 Project Plan & Progress v1.0 | Provides project governance and phase structure. |
| 13 Research Synthesis v1.0 | Drives research/benchmark/dependency adoption tasks. |
| 14 Architecture Decision Matrix v1.0 | Constrains backlog architecture decisions. |
| 15 Master Architecture v1.0 | Provides master component/dependency map. |
| 16 Repository Blueprint v1.0 | Defines physical locations for implementation. |
| 17 Technology Decisions v1.0 | Defines technology defaults and deferred evaluations. |
| 18 Implementation Plan v1.0 | Provides the phase sequence, gates and Definition of Done operationalized by this backlog. |

# 36. Initial Implementation Start Set

| Order | Start with | Why |
| --- | --- | --- |
| 1 | T001–T010 | Make repository reproducible. |
| 2 | T011–T020 | Create stable contracts/state. |
| 3 | T021–T030 | Establish security boundary. |
| 4 | T031–T040 | Establish one authorization path. |
| 5 | T041–T049 | Enable safe side effects. |

Do not jump directly to agent autonomy. P6 agent work becomes meaningful only after the control, execution and context foundations are working and tested.

# 37. Final Backlog Snapshot

| Area | Tasks | Priority | Gate |
| --- | --- | --- | --- |
| Foundation | T001–T010 | P0/P1 | G0 |
| Contracts/State | T011–T020 | P0/P1 | G1 |
| Security/Scope | T021–T030 | P0 | G2 |
| Tools/Policy | T031–T040 | P0 | G3 |
| Execution | T041–T049 | P0/P1 | G4 |
| Repository | T050–T055 | P1/P2 | G5 |
| Context/Memory | T056–T065 | P0/P1 | G5 |
| Agent/Model | T066–T075 | P0/P1/P2 | G6 |
| Validation/Recovery | T076–T086 | P0 | G7 |
| Evidence | T087–T094 | P0/P1 | G8 |
| Clients | T095–T104 | P0/P1 | G9 |
| Hardening | T105–T114 | P0/P1 | G10 |
| Release | T115–T120 | P0/P1 | G11 |
| Deferred | T121–T127 | P1/P2/P3 | As triggered |

# 38. Final Status

STATUS: FINAL / LOCKED — v1.0

Task Backlog v1.0 is the canonical implementation work-item baseline for the AI Software Co-Agent. It translates the locked specification, architecture, repository, technology and implementation-plan baselines into ordered epics/tasks, dependencies, gates, acceptance criteria, security rules, progress reporting, evidence requirements and release-blocking work.

— END OF TASK BACKLOG v1.0 —